## dailytasklist
DAILY Task List
| TASKS | STATUS | DUE DATE
2025-07-29 | Immich Workflow Documentation Study | ✅ Complete | 2025-08-01
| Immich Workflow Flowchart | 🏃 In progress | 2025-08-01
| Image Clustering Model Study | ✅ Complete | 2025-08-01
| Technical Documentation – immich_face_recognition.md | 🏃 In progress | 2025-08-01
| Immich Machine Learning Code Study | 🏃 In progress | 2025-08-01
| Setting Environments | ✅ Complete | 2025-08-01
2025-07-30 | Immich Workflow Flowchart | ❌ On hold | 2025-08-01
| Immich Machine Learning Code Study | 🏃 In progress | 2025-08-01
| Face Detection, Cropping, and Recognition Code Study | ✅ Complete | 2025-08-01
2025-07-31 | Immich Machine Learning Code Study | ✅ Complete | 2025-08-01
| Technical Documentation – immich_face_recognition.md | ✅ Complete | 2025-08-01
| Immich Workflow Flowchart | 🏃 In progress | 2025-08-01
| Immich Servers and Architectures Study | 🏃 In progress | 2025-08-01
2025-08-01
2025-08-02
2025-08-03
2025-08-04

## Status
Status
⚠️Not started
🏃 In progress
✅ Complete
❌ On hold

## Models
Models/Frameworks | Path | Line # | Code | Column1
FastAPI for image inference | machine-learning/immich_ml/main.py | 165 | @app.post("/predict", dependencies=[Depends(update_state)])
Executes Predictions | machine-learning/immich_ml/main.py | 181 | async def run_inference(payload: Image ¦ str, entries: InferenceEntries) -> InferenceResponse:
Server Shutdown - no more BG tasks | machine-learning/immich_ml/main.py | 245 | async def idle_shutdown_task() -> None:
RetinaFace Model Load | machine-learning/immich_ml/main.py | 92-97 | if preload.facial_recognition.detection is not None: await load_models(preload.facial_recognition.detection, ModelType.DETECTION, ModelTask.FACIAL_RECOGNITION, )
ArcFaceONNX model load | machine-learning/immich_ml/main.py | 99-104 | if preload.facial_recognition.recognition is not None: await load_models( preload.facial_recognition.recognition, ModelType.RECOGNITION, ModelTask.FACIAL_RECOGNITION, )
RetinaFace | machine-learning/immich_ml/models/facial_recognition/detection.py | 4 | from insightface.model_zoo import RetinaFace
Input Decoding | machine-learning/immich_ml/models/facial_recognition/detection.py | 28 | inputs = decode_cv2(inputs)
Detection Threshold - minscore | machine-learning/immich_ml/models/facial_recognition/detection.py | 16, 17 | min_score: float = 0.7,
RetinaFace Model Load | machine-learning/immich_ml/models/facial_recognition/detection.py | 22, 23 | self.model = RetinaFace(session=session) self.model.prepare(ctx_id=0, det_thresh=self.min_score, input_size=(640, 640))
ArcFaceONNX | machine-learning/immich_ml/models/facial_recognition/recognition.py | 7 | from insightface.model_zoo import ArcFaceONNX
Image crop and affine transformations | machine-learning/immich_ml/models/facial_recognition/recognition.py | 8 | from insightface.utils.face_align import norm_crop | def norm_crop(img, landmark, image_size=112, mode='arcface'): M = estimate_norm(landmark, image_size, mode) warped = cv2.warpAffine(img, M, (image_size, image_size), borderValue=0.0) return warped
Embedding Normalization | machine-learning/immich_ml/models/facial_recognition/recognition.py | 15 | from immich_ml.models.transforms import decode_cv2, serialize_np_array
ArcFaceONNX model load | machine-learning/immich_ml/models/facial_recognition/recognition.py | 41 | self.model = ArcFaceONNX(self.model_path_for_format(ModelFormat.ONNX).as_posix(), session=session,)
Image crop | machine-learning/immich_ml/models/facial_recognition/recognition.py | 77 | return [norm_crop(image, landmark) for landmark in faces["landmarks"]]
Crop Image and Embeddings size | machine-learning/immich_ml/sessions/rknn/__init__.py | 38 | "recognition": {"input": {"norm_tensor:0": (1, 3, 112, 112)}, "output": {"norm_tensor:1": (1, 512)}},

## Server
Server
The Immich backend is divided into several services, which are run as individual docker containers.
1. immich-server - Handle and respond to REST API requests, execute background jobs (thumbnail generation, metadata extraction, transcoding, etc.)
2. immich-machine-learning - Execute machine learning models
3. postgres - Persistent data storage
4. redis- Queue management for background jobs