## dailytasklist
DAILY TASKS
| TASKS | STATUS | DUE DATE
2025-07-29 | Immich Workflow Documentation Study | ✅ Complete | 2025-08-01
| Immich Workflow Flowchart | 🏃 In progress | 2025-08-01
| Research Image Clustering Model | ✅ Complete | 2025-08-01
| Technical Documentation – immich_face_recognition.md | 🏃 In progress | 2025-08-01
| Immich Machine Learning Code Study | 🏃 In progress | 2025-08-01
| Setting Environments | ✅ Complete | 2025-08-01
2025-07-30 | Immich Workflow Flowchart | ❌ On hold | 2025-08-01
| Immich Machine Learning Code Study | 🏃 In progress | 2025-08-01
| Face Detection, Cropping, and Recognition Code Study | ✅ Complete | 2025-08-01
2025-07-31 | Immich Machine Learning Code Study | ✅ Complete | 2025-08-01
| Technical Documentation – immich_face_recognition.md | ✅ Complete | 2025-08-01
| Immich Workflow Flowchart | ✅ Complete | 2025-08-01
| Immich Servers and Architectures Study | 🏃 In progress | 2025-08-06
| Immich Code Environment Setup With Docker | ✅ Complete | 2025-08-06
| Immich Code Environment Setup Without Docker | ❌ On hold | 2025-08-06
2025-08-01 | Research on Immich | ✅ Complete | 2025-08-01
2025-08-05 | SQL Database Created | ✅ Complete | 2025-08-08
| SQL Tables Created | 🏃 In progress | 2025-08-08
| SQL Tables Relationship Building | ✅ Complete | 2025-08-08
| Settup the File System (Directories and images) | ✅ Complete | 2025-08-08
| Documentation README.md | 🏃 In progress | 2025-08-08
2025-08-06 | Documentation README.md for SQL database building | ✅ Complete | 2025-08-08
| SQL Tables Created | ✅ Complete | 2025-08-08
| Sample Data Insertion | ✅ Complete | 2025-08-08
| Connect to the database with Python | ✅ Complete | 2025-08-15
| Python script that reads unprocessed media entries from the SQL Server database | ✅ Complete | 2025-08-15
| Face Detection Module of Immich Implementation | 🏃 In progress | 2025-08-15
2025-08-07 | Python Setup for Retinaface | ✅ Complete | 2025-08-15
| Retina Face Implementation in Python | ✅ Complete | 2025-08-15
| Face Cropping | ✅ Complete | 2025-08-15
| Pre-Processing and Post processing of Input and Output | ✅ Complete | 2025-08-15
| Database Update after new entry of thumbnails | ✅ Complete | 2025-08-15
| Documentation | 🏃 In progress | 2025-08-15
| config.py file implementation | 🏃 In progress | 2025-08-15
| SQL Query Processing through Python | ✅ Complete | 2025-08-15
2025-08-08 | Cropping the image face using IMMICH methodology | 🏃 In progress | 2025-08-15
| Documentation | 🏃 In progress | 2025-08-15
| config.py file implementation | ✅ Complete | 2025-08-15
| main.py file setup | ✅ Complete | 2025-08-15
| Documentation of requirements.txt | ✅ Complete | 2025-08-15
2025-08-11 | Affine Transformation Implementation (Face Alignment) | ✅ Complete | 2025-08-15
| Cropping the face and Implementation of Margin | ✅ Complete | 2025-08-15
| Documentation README.md | ✅ Complete | 2025-08-15
2025-08-12 | Demo Video making and editing | ✅ Complete | 2025-08-15
| Database Created based on new architecture | ✅ Complete | 2025-08-22
| Embedding generating | 🏃 In progress | 2025-08-22
| Implementation of DBSCAN in clustering | 🏃 In progress | 2025-08-22
2025-08-13 | Image cropping issues resolving | ✅ Complete | 2025-08-15
| Embedding generating | 🏃 In progress | 2025-08-22
| Implementation of DBSCAN in clustering | 🏃 In progress | 2025-08-22
| openl3 for clustering | 🏃 In progress | 2025-08-22
| CLIP encoder for embedding generation | 🏃 In progress | 2025-08-22
2025-08-15 | Embedding Generation (FaceNet) | ✅ Complete | 2025-08-22
| Clustering (DBSCAN) | 🏃 In progress | 2025-08-22
| Clustering (HDBSCAN) | 🏃 In progress | 2025-08-22
2025-08-18 | Clustering (DBSCAN) | ✅ Complete | 2025-08-22
| Database Update (Faces, and Persons) | ✅ Complete | 2025-08-22
| Reclustering | ✅ Complete | 2025-08-22
| Automation of Detection and Recognition Pipelines | ✅ Complete | 2025-08-22
| Documentation file - README.md | ✅ Complete | 2025-08-22
| Troubleshooting - Persons table (Foreign Key Problems) | 🏃 In progress | 2025-08-22
2025-08-19 | Documentation README.md - editted | ✅ Complete | 2025-08-22
| Troubleshooting - Persons table (Foreign Key Problems) | ✅ Complete | 2025-08-22
| Demo Video making and editing - Detection & Recognition Automated Pipeline | ✅ Complete | 2025-08-22
| Troubleshooting - Log File Generation | ✅ Complete | 2025-08-22
| Face Recognition System - with automated processing | ✅ Complete | 2025-08-22
| Reclustering - DBSCAN+Cosine similarity | ✅ Complete | 2025-08-22
| Jupyter Notebook - Face_Recognition_System(FRS).ipynb | 🏃 In progress | 2025-08-22
2025-08-20 | Demo Video making and editing - Detection & Recognition Automated Pipeline (processing and results) | ✅ Complete | 2025-08-22
| Jupyter Notebook - Face_Recognition_System(FRS).ipynb | 🏃 In progress | 2025-08-22
| Troubleshooting - Re-Clustering Module | ✅ Complete | 2025-08-22
2025-08-21 | Jupyter Notebook - Face_Recognition_System(FRS).ipynb | ✅ Complete | 2025-08-22
| Testing - Face Recognition System | ✅ Complete | 2025-08-22
2025-08-21 | Video Face Recognition - Code Study | 🏃 In progress
| Normalized Point based cropping | 🏃 In progress
2025-08-25 | Normalized Point based cropping - Execution & Comparison | ✅ Complete | 2025-08-25
| Manual Documentation | ✅ Complete | 2025-08-25
| Video Editing - Automation Pipeline | ✅ Complete | 2025-08-25
| Flowchart Editing | ✅ Complete | 2025-08-25
2025-08-26 | Automate DB - in case of reclustering | ✅ Complete | 2025-08-26
| CLI options: --recluster, --dry-run. | ✅ Complete | 2025-08-26
| Portrait Generation | ✅ Complete | 2025-08-26
| Update Portrait Id in Database | ✅ Complete | 2025-08-26
2025-08-27 | Troubleshooting - Face Recognition System | ✅ Complete | 2025-09-02
| Manual Improvement | 🏃 In progress | 2025-09-02
| Github Repo Improvement | 🏃 In progress | 2025-09-02
2025-08-28 | Manual Improvement | 🏃 In progress | 2025-09-02
| Github Repo Improvement | ✅ Complete | 2025-09-02
| Initial Study - How to Dockerize? | 🏃 In progress | 2025-09-02
2025-08-29 | Dockerization | 🏃 In progress | 2025-09-02
2025-09-01 | Dockerization | 🏃 In progress | 2025-09-02
| Server Connectivity | 🏃 In progress | 2025-09-02
2025-09-02 | Dockerization | ✅ Complete | 2025-09-02
| Server Connectivity | ✅ Complete | 2025-09-02
| Documentation in README.md files for folders in github | ✅ Complete | 2025-09-02
2025-09-03 | Troubleshooting : Dockerization | 🏃 In progress | 2025-09-05
2025-09-04 | Troubleshooting : Dockerization - File path ammendments | ✅ Complete | 2025-09-05
| Manual Updates : Dockerization | ✅ Complete | 2025-09-05
| Copy the created thumbnail folder from container to local machine and local machine to container : Synchronous | ✅ Complete | 2025-09-05
| Github Repo Improvement & Updates | 🏃 In progress | 2025-09-05
2025-09-05 | Troubleshooting : Dockerization | ✅ Complete | 2025-09-05
| Github Repo Improvement & Updates | ✅ Complete | 2025-09-05
| Cache the downloads | ✅ Complete | 2025-09-05
| Download .tar of sql server image and load | ✅ Complete | 2025-09-05
| Situational Logic Implementation : Thumbnail in db but not in folder | ✅ Complete | 2025-09-05
| Conditional Logic Implementation : Image or Video | ✅ Complete | 2025-09-05
| Github Repo Improvements & Updates | ✅ Complete | 2025-09-05
2025-09-08 | Video Making | ✅ Complete | 2025-09-12
| Testing & Debugging - Dockerized Face Recognition System | ✅ Complete | 2025-09-12
| Dockarized Container : py files hidden | 🏃 In progress | 2025-09-12
| Video Editing | 🏃 In progress | 2025-09-12
2025-09-09 | Dockarized Container : py files hidden --> PYC files | 🏃 In progress | 2025-09-12
| Situational Logic Implementation : dbo.MediaItems show image is processed but not stored in dbo.Faces | 🏃 In progress | 2025-09-12
| Github Repo Improvements & Updates | 🏃 In progress | 2025-09-12
2025-09-10 | Dockarized Container : py files hidden --> multiple PYC files | ✅ Complete | 2025-09-12
| Dockarized Container : py files hidden --> single PYC files | ✅ Complete | 2025-09-12
| .exe of Face Recognition System | 🏃 In progress | 2025-09-12
2025-09-11 | .exe of Face Recognition System | 🏃 In progress | 2025-09-12
| Logo for .exe | ✅ Complete | 2025-09-12
| Packages management in .exe | 🏃 In progress | 2025-09-12
2025-09-12 | Logo Finalization | ✅ Complete | 2025-09-12
| .exe of Face Recognition System | ✅ Complete | 2025-09-12
| .env setup for .exe | ✅ Complete | 2025-09-12
| Set --recluster flag for everyrun | ✅ Complete | 2025-09-12
2025-09-15 | .exe of Face Recognition System - Updated | ✅ Complete | 2025-09-15
| Video Making and Editing of .exe execution | ✅ Complete | 2025-09-15
| Manual Improvements | 🏃 In progress | 2025-09-16
2025-09-16 | Manual Improvements | ✅ Complete | 2025-09-16
| GitHub Improvements | ✅ Complete | 2025-09-16
| Files Check | ✅ Complete | 2025-09-16
| Immich: Video upload check with face detection, recognition, and clustering. | ✅ Complete | 2025-09-19
2025-09-17 | Study Video Processing in Immich & PhotoPrism | ✅ Complete | 2025-09-19
2025-09-18 | Study Video Processing in DeepStack, & CompreFace | ✅ Complete | 2025-09-19
| Study Video Processing in Double-Take | 🏃 In progress | 2025-09-19

## Status
Status
⚠️Not started
🏃 In progress
✅ Complete
❌ On hold

## Models
Models/Frameworks | Path | Line # | Code | Column1
FastAPI for image inference | machine-learning/immich_ml/main.py | 165 | @app.post("/predict", dependencies=[Depends(update_state)])
Executes Predictions | machine-learning/immich_ml/main.py | 181 | async def run_inference(payload: Image ¦ str, entries: InferenceEntries) -> InferenceResponse:
Server Shutdown - no more BG tasks | machine-learning/immich_ml/main.py | 245 | async def idle_shutdown_task() -> None:
RetinaFace Model Load | machine-learning/immich_ml/main.py | 92-97 | if preload.facial_recognition.detection is not None: await load_models(preload.facial_recognition.detection, ModelType.DETECTION, ModelTask.FACIAL_RECOGNITION, )
ArcFaceONNX model load | machine-learning/immich_ml/main.py | 99-104 | if preload.facial_recognition.recognition is not None: await load_models( preload.facial_recognition.recognition, ModelType.RECOGNITION, ModelTask.FACIAL_RECOGNITION, )
RetinaFace | machine-learning/immich_ml/models/facial_recognition/detection.py | 4 | from insightface.model_zoo import RetinaFace
Input Decoding | machine-learning/immich_ml/models/facial_recognition/detection.py | 28 | inputs = decode_cv2(inputs)
Detection Threshold - minscore | machine-learning/immich_ml/models/facial_recognition/detection.py | 16, 17 | min_score: float = 0.7,
RetinaFace Model Load | machine-learning/immich_ml/models/facial_recognition/detection.py | 22, 23 | self.model = RetinaFace(session=session) self.model.prepare(ctx_id=0, det_thresh=self.min_score, input_size=(640, 640))
ArcFaceONNX | machine-learning/immich_ml/models/facial_recognition/recognition.py | 7 | from insightface.model_zoo import ArcFaceONNX
Image crop and affine transformations | machine-learning/immich_ml/models/facial_recognition/recognition.py | 8 | from insightface.utils.face_align import norm_crop | def norm_crop(img, landmark, image_size=112, mode='arcface'): M = estimate_norm(landmark, image_size, mode) warped = cv2.warpAffine(img, M, (image_size, image_size), borderValue=0.0) return warped
Embedding Normalization | machine-learning/immich_ml/models/facial_recognition/recognition.py | 15 | from immich_ml.models.transforms import decode_cv2, serialize_np_array
ArcFaceONNX model load | machine-learning/immich_ml/models/facial_recognition/recognition.py | 41 | self.model = ArcFaceONNX(self.model_path_for_format(ModelFormat.ONNX).as_posix(), session=session,)
Image crop | machine-learning/immich_ml/models/facial_recognition/recognition.py | 77 | return [norm_crop(image, landmark) for landmark in faces["landmarks"]]
Crop Image and Embeddings size | machine-learning/immich_ml/sessions/rknn/__init__.py | 38 | "recognition": {"input": {"norm_tensor:0": (1, 3, 112, 112)}, "output": {"norm_tensor:1": (1, 512)}},

## Server
Server
The Immich backend is divided into several services, which are run as individual docker containers.
1. immich-server - Handle and respond to REST API requests, execute background jobs (thumbnail generation, metadata extraction, transcoding, etc.)
2. immich-machine-learning - Execute machine learning models
3. postgres - Persistent data storage
4. redis- Queue management for background jobs